## About (hidden)
About this workbook
Guide for screen readers
There are 4 worksheets in this workbook. Infographic Timeline Chart Data About Chart Data (hidden) The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
Helpful information
This Inforgraphic Timeline charts 5 significant milestones and their activities or descriptions on a timeline. To modify or add timelines, simply update the table in the Chart Data worksheet.
You can chart infomration by year, by day month values or create a blank space to place an icon or text box. Simply select the method you want in Chart Data worksheet cell D2.
This is the last instruction in this worksheet.

## Chart Data
Create an infographic timeline by entering important milestones and activities in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Infographic Chart Data
Select how to show dates in the chart by selecting "Year" or "Day Month" in the dropdown list in cell D2. | Chart Milestones by Year, Day Month, or leave blank. Select an option at right: |  | Day Month
Headings for the table Chart Data is in cells B3 through D3. | Date | Milestone Title | Description or Activity
Enter a milestone dates in cells B4 through B8. Enter milestone title in cells C4 through C8. Enter milestone description or activity in cells D4 through D8. This is the last instruction in this worksheet. | 2020-06-10 | Phase 1 Begins | Primary Inputs: OSC Assessment Request Received by C3PAO Activities: 1.1 Analyze Requirements 1.2 Develop Assessment Plan 1.3 Verify Readiness to Conduct Assessment
| 2020-06-20 | Phase 1 Ends | Primary Outputs: A. Agreed-upon and Requirements, Assessment Plan and Schedule B. Pre-Assessment Results, including Go/No Go decision C. Mappings, Diagrams, etc. of Objective Evidence (controls and processes) D. Participant Briefing (Delivered)
| 2020-06-21 | Phase 2 Begins | Primary Inputs: All Outputs From Phase 1 Activities: 2.1 Collect and Examine OE 2.2 Rate Practices and Validate Preliminary Results 2.3 Generate Final Recommended Assessment Results
| 2020-06-29 | Phase 2 Ends | Primary Outputs: Final Plan and Schedule Practice Characterizations Validated Final Findings Recommended Maturity Level
| 2020-06-30 | Phase 3 Begins | Primary Inputs: All Outputs from Phase 2 Primary Activities: 3.1 Deliver Recommended Assessment Results 3.2 Package and Archive Assessment Assets
| 2020-06-30 | Phase 3 Ends | Primary Outputs: Final Plan and Schedule Practice Characterizations Final Findings Recommended Maturity Level Other C3PAO and AB Reporting Requirements?
| 2020-07-01 | Phase 4 Begins (If Applicable) | Primary Inputs: All Outputs from Phase 2-3 Primary Activities: 4.1 Identify Remediation Approach 4.2 Execute Remediation Approach and Review Maximum Phase 4 TimeFrame: 90 days
Formulas:
Date = [Date, row above]+10

## Infographic Timeline
An Inforgraphic Timeline is in this worksheet starting in cell B1. 5 teardrop shapes with milestone titles above them and milestone dates within them are mapped along a curved line that charts the year from start to end. Next to each teardrop is a description or list of activities for each milestone or informational marker. To modify the content in this worksheet, update the Chart Data table in the Chart Data worksheet. There are no further instructions in this worksheet.
Primary Inputs: OSC Assessment Request Received by C3PAO Activities: 1.1 Analyze Requirements 1.2 Develop Assessment Plan 1.3 Verify Readiness to Conduct Assessment
Primary Inputs: All Outputs From Phase 1 Activities: 2.1 Collect and Examine OE 2.2 Rate Practices and Validate Preliminary Results 2.3 Generate Final Recommended Assessment Results
Primary Outputs: Final Plan and Schedule Practice Characterizations Validated Final Findings Recommended Maturity Level
Primary Inputs: All Outputs from Phase 2 Primary Activities: 3.1 Deliver Recommended Assessment Results 3.2 Package and Archive Assessment Assets
Primary Outputs: Final Plan and Schedule Practice Characterizations Final Findings Recommended Maturity Level Other C3PAO and AB Reporting Requirements?
Primary Outputs: A. Agreed-upon and Requirements, Assessment Plan and Schedule B. Pre-Assessment Results, including Go/No Go decision C. Mappings, Diagrams, etc. of Objective Evidence (controls and processes) D. Participant Briefing (Delivered)
10 Jun
21 Jun
29 Jun
30 Jun
2020
# of Days Dependent on Scope
Phase 1 Begins
Phase 2 Begins
Phase 2 Ends
Phase 3 Begins
Phase 3 Ends
Max. 30 Days Prior to Phase 2 Start with Minimum of 10 days
.5 to 1 Business Day
Phase 1 Ends
6/20/20
Primary Inputs: All Outputs from Phase 2-3 Primary Activities: 4.1 Identify Remediation Approach 4.2 Execute Remediation Approach and Review Maximum Phase 4 TimeFrame: 90 days
Phase 4 Begins (If Applicable)
1 Jul
30 Jun
90 Days Maximum

## Chart Data Hidden (hidden)
Data in this worksheet is used for charting the date in day month format and for charting the year along the roadmap within the Infographic Timeline. Do not delete this worksheet. Modifying or deleting data will affect the integrity of the chart in the Infographic Timeline worksheet. | Chart Data (Hidden) - Do NOT delete this worksheet
Table headers are in cells B2 and D2. | Date | Year
The first date from the Chart Data worksheet is in cell B3 and subsequent cells in that column. The year in cell D3 represents the starting position year of the timeline. | 10 Jun | 2020 | <-- year for the starting position of the roadmap
The year in cell D4 represents the middle position year of the timeline. | 21 Jun | # of Days Dependent on Scope | <-- year for the middle period of the roadmap, note, this may be blank if it's the same year as the starting position of the roadmap
The year in cell D5 represents the last position year of the timeline. This is the last instruction in this worksheet. | 29 Jun |  | <-- year for the last position of the roadmap, note, this may be blank if it's the same year as the starting position of the roadmap
30 Jun
30 Jun
1 Jul
Min. 30 Days Prior to Phase 2
90 Days Maximum