## Phase 1 - Plan and Prepare
CMMC Assessment Method Checklist
Phase 1 - Plan and Prepare for Assessment |  | Checklist Parameters and RACI
Activities | Description | Nominal Days Prior to Onsite | Estimated Duration | C3PAO Organization | Lead Assessor | Assessment Team | OSC POC/Sponsor | CMMC AB | Questions/Comments
1.1 Analyze Requirements | These activities are iterative with the other activities in this Phase to get to initial scoping agreement and pricing. Scoping may be initially difficult based on OSC understanding of what this is all about, planning is always more difficult with an inexperienced POC, C3PAO and the LA can’t control how long it takes the OSC POC to complete 1.16, etc. |  | .5-2 days, pending scope | [5 empty] | Time requirements listed in plan prepare is 1.5 - 6 days. Pricing being communicated has implied a fairly economical cost. Man hours have already exceeded 3K for most just in planning.
1.1.1 | Assessment Request Received by C3PAO from OSC 1. How will lead management happen? | Ideally at least 90 days in advance, minimum 30 days? | Email, marketplace website register, phone call, etc. | Receives |  |  | Initiates |  | Will there be an assessment request form or can use an engagement letter we develop. Standard verbiage. OSC initiated?
1.1.2 | Identify Lead Assessor |  |  | Assigns | Accepts |  | Informed |  | Lead assessor works with OSC POC/Sponsor
1.1.3 | Identify OSC Sponsor |  |  | Informed | Identifies | Informed | Selected
1.1.4 | High Level Scoping (Targets: Organization Seeking Certification (OSC) entity, scope, contract information, Maturity Level, etc.) 1. Need to have pre-assessment planning decision gates (if you don't pass, have supporting artifacts, SSP, network diagrams, mapping to policies, processes, etc.) 2. Need to identify a minimal set of artifacts, etc. (SSPs, etc.) 3. More pre-assessment planning is needed to verify contract requirements - a pre-assessment verification 4. Requirement for OSC to provide contract language to the C3PAO prior to the negotiation of the contract |  | 1-8 hours, depending on scope |  | Leads |  | Agrees |  | Sponsor would have to approve scope with LA. Is this a formalized document? Assumes that Sponsor agrees to scope, but LA has final authority for scoping decisions. Negotiate and provide Rough Order of Magnitude (ROM) of schedule, assessment pricing, dates, etc. and initiate contract for assessment Questions: 1. Will there be pricing guidelines/limits? Travel and Expense policies and guidelines? Answer: AB will not be setting limits or travel expense guidelines 2. Assume the C3PAO will work in conjunction with the Lead Assessor to determine and finalize scoping and pricing. 3. Probably need a standard SOW/BOE, Scoping Template to include a standard list: SSP, network diagram (minimal definition, requirements, already in place, laws on CUI, etc. 4. Assume Levels 1-3 assessments will be onsite (no virtual assessments)
1.1.5 | Determine, Record & Review Assessment Scope and Assessment Objectives |  |  |  | Completes |  | Agrees
1.1.6 | Negotiate and provide Rough Order of Magnitude (ROM) Forr schedule, assessment pricing, dates, etc. and initiate contract for assessment |  |  | Informed | Leads |  | Agrees | Informed
1.1.7 | Identify and Map OSC Processes and Process Roles OSC does this under guidance and in coordination with the LA |  |  |  | Leads |  | Involved |  | "LA must verify and direct this with the POC/Sponsor to determine process scope and who to interview, etc. Might be a heavy lift prior to documentation review and on site visit to define processes and evidence needed for review. On the first round for many OSC's this will be very difficult."
1.1.8 | Verify and Record Objective Evidence (OE) Adequacy and Sufficiency |  |  |  | Lead |  | Involved |  | Assumes that the Assessment method will identify minimum adequacy and sufficiency criteria - this will simply verify that and add any additional as needed
1.1.9 | Determine and Confirm Assessment Outputs |  |  |  | Leads |  | Agrees |  | Standard list: 1. Characterizations of practices, with weaknesses, etc. 2. Final briefing on results 3. Assessment record (abbreviated summary of assessment scope, with characterizations and ratings) Potential Options: 1. Recommendations report, including options for actions 2. Executive briefing
1.2 Development Assessment Plan | Plan must be kept up-to-date throughout all assessment phases |  | .5-2 days, pending scope
1.2.1 | Identify Allowable Tailoring of Assessment Method |  |  |  | Leads |  | Consulted
1.2.2 | Identify OE Collection Approach - e.g., method, techniques, and responsibilities, etc. for collecting and managing OE. |  |  |  | Leads |  | Consulted |  | Need to determine what type of and how much evidence can be reviewed prior to the onsite
1.2.3 | Select Assessment Team Members, if applicable |  |  | Assigns | Selects | Selected | Informed
1.2.4 | Identify Resources and Schedule. |  |  |  | Leads | Informed | Consulted |  | Cost could be removed due to pricing sensitivities, but resources and schedule are needed to run the appraisal. Assume there will be a standard assessment plan template.
1.2.5 | Identify and Manage Conflicts of Interest |  |  |  | Leads | Informed | Consulted
1.2.6 | Identify and Manage Assessment Risks and Their Mitigation/Contigency Plans |  |  |  | Leads | Informed | Consulted |  | Risks for and during the assessment
1.2.7 | Obtain and Record Commitment to the Assessment Plan (Including everytime plan changes significantly). Spell out criteria Should the assessor C3PAO must confirm adequate and appropriate scope before starting. YES, to some level (Define in description) | Minimal 10 days? |  | Informed | Leads | Informed | Agrees | Informed | Lead assessor and Sponsor must agree to and sign the final plan and any major updates. Will the C3PAO confirm adequate and appropriate scope before starting?
1.3 Verify Readiness to Conduct Assessment |  | Minimal 5 days prior? | .5-2 days, pending scope
1.3.1 | Prepare and Train Assessment Team |  |  | Supports | Leads | Receives |  |  | Assume C3PAO provides training materials and the LA schedules, coordinates and delivers it to the team
1.3.2 | Identify, Obtain, Inventory, and Verify OE |  |  |  | Directs | Supports | Completes |  | See comment in Cell J17
1.3.3 | Perform Certification Assessment Readiness Review - Defined as verifying planning and execution preparedness to be able to successfully execute the assessment as planned Verify that all the requirements and condition covered by the assessment plan are met, and conditions - we need to clarify what criteria meets this requirement (mix of self-assessment or 3rd party) |  |  | Informed? | Leads | Supports | Supports
1.3.4 | Update the Assessment Plan and Schedule as Needed, Based on CA-RR |  |  |  | Leads | Supports | Coordinates |  | Will the C3PAO confirm adequate and appropriate scope before starting?

## Phase 2 - Conduct Assessment
CMMC Assessment Method Checklist
Phase 2 - Conduct Assessment |  | Checklist Parameters and RACI
Activities | Description | Nominal Days Prior to Onsite | Estimated Duration | C3PAO Organization | Lead Assessor | Assessment Team | OSC POC | CMMC AB | Questions/Comments
2.1. Collect and Examine OE | This set of activities will be iterative in nature
2.1.1 | Assessment Kickoff-Opening Briefing |  | 1 hour |  | Leads
2.1.2 | Collect and Examine Artifacts - Assumption: Lead Assessor has verified that the organization is prepared for the assessment through a pre-assessment and/or readiness review. |  | Depends on scope |  | Leads | Supports | Provides
2.1.3 | Collect and Examine Affirmations - Lead assessor schedules, works with POC to identify (in Phase 1) who to interview |  |  |  | Leads | Supports | Coordinates
2.1.4 | Observe Control and Procedural Demos (e.g., demonstration that controls are working) |  |  |  | Observes | Observes | Coordinates
2.1.5 | Verify OE and Record Gaps |  |  |  | Leads | Supports
2.1.6 | Update OE Collection Approach |  |  |  | Leads | Supports | Coordinates
2.2 Rate Practices and Validate Preliminary Results
2.2.1 | Determine and Record Initial Model Practice Ratings |  |  |  | Leads | Supports
2.2.2 | Generate Preliminary Findings |  |  |  | Leads | Supports | Coordinates
2.2.3 | Validate Preliminary Findings - Minimum of one event to all participants prior to final findings, but left at discretion of Lead Assessor to do daily validation sessions, check-in on data, etc. |  | 1 hour |  | Leads | Supports |  |  | Separate out? High level daily meetings with Sponsor and/or Participants? Hit list/actions needed to be addressed Need to be cautious about Sponsor desire for wanting to know status - needs boundaries around what can and can't be said, reported, etc.
2.3 Generate Final Recommended Assessment Results
2.3.1 | Determine Final Practice Pass/Fail Results |  |  |  | Leads | Supports
2.3.2 | Determine Maturity Level Recommendation |  |  | Reviews | Leads | Supports |  |  | Assessor awards rating certification, which then must get verified by C3PAO and AB audit of process C3PAO awards certifications
2.3.3 | Create and Finalize Final Findings (Built on validate preliminary findings, practice ratings and ML recommendation) |  |  |  | Leads | Supports | Receives
2.3.4 | Record Final Recommeded Assessment Results |  |  |  | Leads | Supports | Supports

## Phase 3 - Report Results
CMMC Assessment Method Checklist
Phase 3 - Report Assessment Results |  | Checklist Parameters and RACI
Activities | Description | Nominal Days Prior to Onsite | Estimated Duration | C3PAO Organization | Lead Assessor | Assessment Team | OSC POC | CMMC AB | Questions/Comments
3.1 Deliver Recommended Assessment Results
3.1.1 | Deliver Final Findings | N/A | 1 hour |  | Leads | Supports | Receives
3.1.2 | Conduct Tailored/Optional Follow-on Activities, (e.g. Executive Debriefing) |  |  |  | Leads | Supports | Coordinates
3.2 Package and Archive Assessment Assets
3.2.1 | Submit Assessment Results Package |  |  | Receives | Submits |  | Copied | Receives | AB Certified QA auditor will make the call on final maturity level (approval or denial) based on quality audit
3.2.2 | Provide Retrospective Feedback to C3PAO and AB (Surveys?). Goes to AB, C3PAO and LA |  |  | Receives | Submits |  | Copied?
3.2.3 | Archive or Dispose of Any Assessment Artifacts |  |  |  | Leads | Supports | Supports

## Phase 4 - Remediation
CMMC Assessment Method Checklist
Phase 4 Remediation of Outstanding Assessment Issues |  | Checklist Parameters and RACI
Activities | Description | Nominal Days Prior to Onsite | Estimated Duration | C3PAO Organization | Lead Assessor | Assessment Team | OSC POC | CMMC AB | Questions/Comments
4.1 Identify Remediation Approach | [8 empty] | Is there a timeframe/limit for how long after an assessment - no more than 30, 60 or 90 business days? Need criteria here
4.1.1 | Verify and Confirm Outstanding Assessment Issues (Weaknesses) | N/A | 1 hour | Informed? | Leads | Supports | Supports | Verifies?
4.1.2 | Identify Remediation Approach and Update Assessment Plan (Addendum to discuss the deltas only) |  |  |  | Leads | Supports | Coordinates
4.1.3 | Submit remediation approach to C3PAO for verification to proceed |  |  | Reviews and Approves | Submits | Supports | Supports
4.2 Execute Remediation Approach and Review
4.2.1 | Review all outstanding issues against updated OE (documents, demos/tests and interviews) |  |  |  | Leads | Supports? | Supports
4.2.2 | Update Previous Characterizations and Findings as approprate Repeat Activities 2.2.1-2.3.4 where needed Lead Assessor must preserve previous characterizations and ratings for historical baselining |  |  |  | Leads | Supports
4.2.3 | Verify and Determine Remediated Maturity Level Rating |  |  |  | Leads | Supports | Informed
4.2.4 | Report Remediation Results Updated FF to OSC, and then start "delta" package, but need to maintain the original assessment results and the remediation results) |  |  | Informed | Leads | Supports? | Informed | Verifies
4.2.5 | Conduct Remediation Phase 3 Reporting Steps Starting with 3.1.1 Lead Assessor maintains historical baseline of initial results and updated remediation results |  |  |  | Leads | Supports | Informed

## Simplified Checklist
CMMC Assessment
Prepare for Assessment Phase - Technical Kickoff Meeting
Determine all Stakeholders
Review CMMC Level to be tested
Review Test Plan (HW, SW)
Review all artifacts needed for CMMC Level (SSP and appendices)
Review all Security Controls
Review Boundary - ensure it lines up with Test Plan
Review Self-Assessment (Scans, STIGs, Benchmarks, Documents, Control implementation details)
Pre-Assessment Review - Phone Con and Email
Conduct Assessment Phase
Execute Test Plan
Review STIG checks, ACAS, SCAP, Code review, if required
Onsite review - personnel interviews - Sys Admins etc.
Re-review any failed controls (STIGs may flag some)
Perform Risk Assessment
Prepared Security Assessment Report (SAR)
Save SAR as PDF sign and upload as formal artifact
Upload all assessment files as a zip file
Post Assessment Phase
Out Brief of Results and Submission